## Board
STORIES | NOT DONE | IN PROGRESS... | DONE | DROPPED
STORY # 01:
Voice Calls
STORY # 01 - TASK # 04:
TestVoiceCall
STORY # 01 - TASK # 06:
Implement Display
STORY # 01 - TASK # 03:
MakeVoiceCallService, ReceiveVoiceCallService & FinishVoiceCallService
STORY # 01 - TASK # 01:
Update Domain
STORY # 01 - TASK # 05:
Update WSDL Contract
STORY # 02:
Video Calls
STORY # 01 - TASK # 02:
Update Bridges
STORY # 01 - TASK # 07:
Implement Handlers
STORY # 02 - TASK # 04:
TestVideoCall
STORY # 02 - TASK # 06:
Implement Display
STORY # 02 - TASK # 03:
MakeVideoCallService, ReceiveVideoCallService & FinishVideoCallService
STORY # 02 - TASK # 01:
Update Domain
STORY # 02 - TASK # 05:
Update WSDL Contract
STORY # 02 - TASK # 02:
Update Bridges
STORY # 02 - TASK # 07:
Implement Handlers
STORY # 03:
Last Call Info
STORY # 03 - TASK # 04:
TestLastCall
STORY # 03 - TASK # 06:
Implement Display
STORY # 03 - TASK # 03:
LastCallService
STORY # 03 - TASK # 01:
Update Domain
STORY # 03 - TASK # 05:
Update WSDL Contract
STORY # 03 - TASK # 02:
Update Bridges
STORY # 03 - TASK # 07:
Update Handlers
STORY # 04:
Bonus Offers
STORY # 04 - TASK # 01:
Update Domain
STORY # 04 - TASK # 05:
Update Operator Instantiation
STORY # 04 - TASK # 04:
Update IncreasePhoneBalanceTest & CreateNewOperatorServiceTest
STORY # 04 - TASK # 03:
Update RegisterOperatorService
STORY # 02 - TASK # 02:
Update Bridges
STORY # 04 - TASK # 06:
Update WSDL Contract
STORY # 05:
1st Sprint Bug Fix
STORY # 06:
1st Sprint Refination
STORY # 06 - TASK # 05:
Refine GetLastMadeCommunicationService
STORY # 06 - TASK # 01:
Provide interface for LastMadeCommunication
STORY # 06 - TASK # 07:
Organize and improve tests
STORY # 06 - TASK # 02:
Move SendSMS behaviour to the PhoneState
STORY # 06 - TASK # 03:
Organize exceptions in packages
STORY # 06 - TASK # 04:
Replace substrings to get number prefixes
STORY # 06 - TASK # 08:
Display error messages more appropriately
STORY # 06 - TASK # 09:
Improve communication input and last communication display
STORY # 07:
UDDI Registry
STORY # 07 - TASK # 01:
Update build.xml
STORY # 07 - TASK # 02:
Implement registration, search and deletion
STORY # 07 - TASK # 03:
Minimize UDDI searches
STORY # 08:
Timestamp Storing
STORY # 08 - TASK # 01:
Implement timestamp database
STORY # 08 - TASK # 02:
Implement handlers
STORY # 09:
Packet Ordering
STORY # 09 - TASK # 01:
Number packets
STORY # 09 - TASK # 02:
Order packets
STORY # 10:
Silent Failures
STORY # 11:
Byzantine Failures
STORY # 12:
Certification Authority
STORY # 12 - TASK # 01:
Implement database
STORY # 12 - TASK # 02:
Implement SignCertificateService
STORY # 12 - TASK # 03:
Write WSDL
STORY # 13:
Message Authentication
STORY # 13 - TASK # 01:
Check certificate's time validity
STORY # 13 - TASK # 02:
Validate CA's certificate
STORY # 13 - TASK # 03:
Validate client's digital signature
STORY # 14:
Certificate Revogation
STORY # 14 - TASK # 01:
Implement RevogateCertificateService
STORY # 14 - TASK # 03:
Update WSDL
STORY # 14 - TASK # 02:
Implement GetBlackListService
STORY # 14 - TASK # 04:
Verify if certificates aren't in black list
STORY # 06 - TASK # 06:
Turn representations and verifiers into Singletons
STORY # 05 - TASK # 01: Don't allow state changes in the OccupiedState
STORY # 05 - TASK # 02: Fix video calls
STORY # 10 - TASK # 01:
Implement packet replicator
STORY # 11- TASK # 01:
Implement response voting
STORY # 11- TASK # 02:
Ignore multiple response from the same server
STORY # 10 - TASK # 02:
Implement response merger
STORY # 10 - TASK # 03:
Implement asynchronous calls
STORY # 15:
Timestamp Phones
STORY # 15 - TASK # 01:
Update Domain
STORY # 15 - TASK # 02:
Update Services
STORY # 15 - TASK # 03:
Update WSDL
STORY # 16:
Refine Timestamping
STORY # 16 - TASK # 01:
Update Domain
STORY # 16 - TASK # 02:
Update Services
STORY # 16 - TASK # 03:
Implement SetTimestampService and GetTimestampService
STORY # 17:
Replication Tests
STORY # 17 - TASK # 01:
Test packet replication
STORY # 17 - TASK # 03:
Test silent fault toleration
STORY # 17 - TASK # 02:
Test packet merging
STORY # 17 - TASK # 04:
Test byzantine fault toleration
STORY # 16 - TASK # 04:
Update ApplicationServerWebService
STORY # 16 - TASK # 05:
Update DistributedAnacomServerBridge
STORY # 18 - TASK # 01:
Test SetKeysService
STORY # 18 - TASK # 02:
Test SignCertificateService
STORY # 18 - TASK # 03:
Test BlockCertificateService
STORY # 18 - TASK # 04:
Test GetBlockedListService
STORY # 18 - TASK # 05:
Test SOAP Messages
STORY # 18:
Security Tests
STORY # 19:
3rd Sprint Refination
STORY # 19 - TASK # 01:
Add type distinction in the Communication classes
STORY # 19 - TASK # 02:
Normalize prefix determination
STORY # 19 - TASK # 03: Normalize attribute names
STORY # 19 - TASK # 04:
Normalize service return
STORY # 20:
Bug fix
STORY # 20 - TASK # 01: Fix Replication Bugs
STORY # 20 - TASK # 02: Fix Order Packet Bugs
STORY # 20 - TASK # 03: Fix SecurityHandler Bugs
STORY # 20 - TASK # 04: Fix CAManager Bugs
STORY # 21:
Refactoring
STORY # 21- TASK # 01:
SecurityHandlers refactoring
STORY # 21- TASK # 02:
BizantineProtocolHandler refactoring
STORY # 21- TASK # 03:
SilentFailureProtocolHandler refactoring
STORY # 22:
Write Reports
STORY # 22 - TASK # 01:
Write ES Report
STORY # 22 - TASK # 02:
Write SD Report

## Availability Estimate
Availability Estimate
weekday | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T
month | April | [14 empty] | May
day | 2012-04-16 | 2012-04-17 | 2012-04-18 | 2012-04-19 | 2012-04-20 | 2012-04-21 | 2012-04-22 | 2012-04-23 | 2012-04-24 | 2012-04-25 | 2012-04-26 | 2012-04-27 | 2012-04-28 | 2012-04-29 | 2012-04-30 | 2012-05-01 | 2012-05-02 | 2012-05-03 | 2012-05-04 | 2012-05-05 | 2012-05-06 | 2012-05-07 | 2012-05-08 | 2012-05-09 | 2012-05-10 | 2012-05-11 | 2012-05-12 | 2012-05-13 | 2012-05-14 | 2012-05-15
Resource | Sprint #1 | [6 empty] | Sprint #2 | [6 empty] | Sprint #3 | [6 empty] | Sprint #4 | [6 empty] | Sprint #5 |  | Total per Resource
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Alexandre | 0 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 8 | 9 | 72
Emídio | 0 | 2 | 2 | 0 | 2 | 2 | 2 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 9 | 9 | 65
João | 0 | 1 | 1 | 1 | 1 | 3 | 3 | 0 | 1 | 2 | 1 | 1 | 3 | 3 | 1 | 2 | 0 | 2 | 3 | 1 | 0 | 0 | 4 | 0 | 4 | 5 | 8 | 8 | 7 | 8 | 74
Joaquim | 0 | 2 | 1 | 2 | 0 | 3 | 2 | 0 | 2 | 2 | 2 | 1 | 2 | 2 | 0 | 1 | 2 | 2 | 2 | 3 | 3 | 0 | 4 | 4 | 3 | 5 | 8 | 8 | 9 | 6 | 81
Miguel | 0 | 2 | 2 | 0 | 2 | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 0 | 2 | 2 | 2 | 2 | 2 | 3 | 0 | 0 | 2 | 3 | 3 | 3 | 8 | 7 | 67
Rodrigo | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 80
Total per Day | 1 | 9 | 8 | 5 | 7 | 14 | 13 | 5 | 8 | 11 | 10 | 9 | 13 | 13 | 10 | 7 | 9 | 13 | 14 | 13 | 12 | 13 | 18 | 14 | 19 | 23 | 29 | 29 | 46 | 44 | 439
Until the end of the Sprint | 56 | 47 | 39 | 34 | 27 | 13 | 0 | 64 | 56 | 45 | 35 | 26 | 13 | 0 | 68 | 61 | 52 | 39 | 25 | 12 | 0 | 132 | 114 | 100 | 81 | 58 | 29 | 0 | 44 | 0
Total per Sprint | 57 | [6 empty] | 69 | [6 empty] | 78 | [6 empty] | 145 | [6 empty] | 90

## Actual Spent Time
Actual Availability
weekday | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T
month | April | [14 empty] | May
day | 2012-04-16 | 2012-04-17 | 2012-04-18 | 2012-04-19 | 2012-04-20 | 2012-04-21 | 2012-04-22 | 2012-04-23 | 2012-04-24 | 2012-04-25 | 2012-04-26 | 2012-04-27 | 2012-04-28 | 2012-04-29 | 2012-04-30 | 2012-05-01 | 2012-05-02 | 2012-05-03 | 2012-05-04 | 2012-05-05 | 2012-05-06 | 2012-05-07 | 2012-05-08 | 2012-05-09 | 2012-05-10 | 2012-05-11 | 2012-05-12 | 2012-05-13 | 2012-05-14 | 2012-05-15
Resource | Sprint #1 | [6 empty] | Sprint #2 | [6 empty] | Sprint #3 | [6 empty] | Sprint #4 | [6 empty] | Sprint #5 |  | Total per Resource
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Alexandre | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 5 | 1 | 0 | 3 | 1 | 2 | 0 | 0 | 3 | 0 | 0 | 1 | 4 | 12 | 12 | 7 | 7 | 63
Emídio | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 1 | 5 | 0 | 1 | 0 | 0 | 0 | 4 | 3 | 0 | 2 | 4 | 3 | 5 | 7 | 7 | 51
João | 0 | 1 | 0 | 0 | 2 | 2 | 3 | 1 | 0 | 0 | 0 | 2 | 3 | 3 | 2 | 1 | 0 | 0 | 2 | 2 | 2 | 1 | 7 | 0 | 2 | 4 | 12 | 12 | 7 | 7 | 78
Joaquim | 0 | 0 | 4 | 3 | 0 | 1 | 2 | 0 | 2 | 0 | 2 | 0 | 3 | 3 | 2 | 1 | 0 | 0 | 4 | 2 | 1 | 1 | 7 | 0 | 7 | 0 | 4 | 6 | 7 | 7 | 69
Miguel | 0 | 1 | 0 | 2 | 1 | 1 | 5 | 2 | 1 | 2 | 5 | 0 | 3 | 4 | 3 | 0 | 0 | 5 | 0 | 0 | 3 | 3 | 0 | 0 | 3 | 3 | 2 | 4 | 7 | 7 | 67
Rodrigo | 0 | 0 | 4 | 1 | 1 | 1 | 3 | 2 | 2 | 3 | 4 | 2 | 1 | 2 | 3 | 4 | 0 | 4 | 0 | 1 | 3 | 4 | 2 | 1 | 6 | 4 | 4 | 8 | 7 | 7 | 84
Total per Day | 0 | 2 | 12 | 8 | 4 | 6 | 13 | 5 | 7 | 7 | 12 | 6 | 10 | 17 | 12 | 11 | 3 | 11 | 8 | 5 | 9 | 16 | 19 | 1 | 21 | 19 | 37 | 47 | 42 | 42 | 412
Until the end of the Sprint | 45 | 43 | 31 | 23 | 19 | 13 | 0 | 59 | 52 | 45 | 33 | 27 | 17 | 0 | 47 | 36 | 33 | 22 | 14 | 9 | 0 | 144 | 125 | 124 | 103 | 84 | 47 | 0 | 42 | 0
Total per Sprint | 45 | [6 empty] | 64 | [6 empty] | 59 | [6 empty] | 160 | [6 empty] | 84

## Product BackLog
Product BackLog
Stories
State | Name | Description | Points
Done! | Voice Calls | Establish voice calls between two phones | 13
Done! | Video Calls | Establish video calls between two phones | 13
Done! | Last Call Info | Display the information of the last call established by the phone | 5
Done! | Bonus Offers | Offer bonuses when a client increases its balance | 3
Done! | 1st Sprint Bug Fix | Fix bugs in the 1st sprint | 1
Done! | 1st Sprint Refination | Improve the code from the 1st sprint | 13
Done! | UDDI Registry | Allow for the presentation server to discover application server URLs dinamicly | 8
Dropped | Timestamp Storing | Store timestamps along with the data in the database | 13
Done! | Packet Ordering | SOAP messages are numbered in the presentation server and ordered in the receiver | 8
Done! | Silent Failures | Tolerate one silent failure in an Operator's servers | 13
Done! | Byzantine Failures | Tolerate one byzantine failure in an Operator's servers | 13
Done! | Certification Authority | Provide a service for certification of application servers' public keys | 13
Done! | Message Authentication | Sign SOAP messages and validate signatures | 8
Done! | Certificate Revogation | Allow servers to revogate their certificates and generate new private and public keys | 13
Done! | Timestamp Phones | Allow timestamps to be stored along with Phones | 13
Done! | Refine Timestamping | Timestamps will be moved from Phone to Network and local services will be implemented to manipulate this timestamp | 8
Done! | Replication Tests | Implement jUnit test cases for replication and fault toleration | 21
Done! | Security Tests | Implement jUnit test cases for the Certification Authority and security | 21
Done! | 3th Sprint Refination | Improve the code from the 3rd sprint | 8
Done! | Bug Fix | Fix general project bugs | 21
Done! | Refactoring | Refactorig extensive code | 8
Done! | Write Reports | Write ES and SD reports. | 5
Note on B2: A prioritized list of high-level requirements.
Note on B4: INVEST in stories: - Independent - Negotiable - Valuable - Estimable - Small - Testable

## 1st Sprint
|  |  |  | 37 | M | T | W | R | F | S | S
Story | Task | Category | Who | 5 | Time to finish task (person/hour)
|  |  |  | Estimate | 2012-04-16 | 2012-04-17 | 2012-04-18 | 2012-04-19 | 2012-04-20 | 2012-04-21 | 2012-04-22
Ideal Execution |  |  |  | 34 | 27.2 | 20.4 | 13.6 | 6.8 | 0 | 0 | 0
Total per Day |  |  |  | 34 | 33 | 31 | 27 | 16 | 12 | 7 | 0
Voice Calls | Update Domain | Domain | João | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0
| Update Bridges | Service | João | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| MakeVoiceCallService, ReceiveVoiceCallService & FinishVoiceCallService | Service | João e Miguel | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| TestVoiceCall | Testing | Miguel | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Update WSDL Contract | Distribution | João | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Implement Display | Presentation | Joaquim e Rodrigo | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Implement Handlers | Presentation | Joaquim e Rodrigo | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0
Video Calls | Update Domain | Domain | Miguel | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0
| Update Bridges | Service | Miguel | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  |  | M | T | W | R | F | S | S
| MakeVideoCallService, ReceiveVideoCallService & FinishVideoCallService | Service | João e Miguel | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 |  | Estimate | 2012-04-16 | 2012-04-17 | 2012-04-18 | 2012-04-19 | 2012-04-20 | 2012-04-21 | 2012-04-22
| TestVideoCall | Testing | Rodrigo | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0
| Update WSDL Contract | Distribution | João | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Implement Display | Presentation | Joaquim e Rodrigo | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Implement Handlers | Presentation | Joaquim e Rodrigo | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0
Last Call Info | Update Domain | Domain | Alexandre e Emídio | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | Ideal | 34 | 27.2 | 20.4 | 13.6 | 6.8 | 0 | 0 | 0
| Update Bridges | Service | Alexandre e Emídio | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | Real | 34 | 33 | 31 | 27 | 16 | 12 | 7 | 0
| LastCallService | Service | Alexandre e Emídio | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | Domain | 6 | 6 | 4 | 4 | 2 | 0 | 0 | 0
| TestLastCall | Testing | Joaquim | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | Service | 8 | 8 | 8 | 8 | 4 | 3 | 1 | 0
| Update WSDL Contract | Distribution | Alexandre e Emídio | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | Presentation | 9 | 8 | 8 | 4 | 2 | 2 | 0 | 0
| Implement Display | Presentation | Alexandre e Emídio | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | Distribution | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 0
| Update Handlers | Presentation | Alexandre e Emídio | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | Testing | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 0
Bonus Offers | Update Domain | Domain | Joaquim | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | Bug-Fix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Update Bridges | Service | Emídio | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
| Update RegisterOperatorService | Service | Joaquim | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
| Update IncreasePhoneBalanceTest & CreateNewOperatorServiceTest | Testing | Alexandre | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| Update Operator Instantiation | Distribution | Rodrigo | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
| Update WSDL Contract | Distribution | Alexandre | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
Note on C3: SMART Tasks: - Specific - Measurable - Achievable - Relevant - Time-Boxed

## 2nd Sprint
|  |  |  | 25 | M | T | W | R | F | S | S
Story | Task | Category | Who | 5 | Time to finish task (person/hour)
|  |  |  | Estimate | 2012-04-23 | 2012-04-24 | 2012-04-25 | 2012-04-26 | 2012-04-27 | 2012-04-28 | 2012-04-29
Ideal Execution |  |  |  | 38 | 30.4 | 22.8 | 15.2 | 7.6 | 0 | 0 | 0
Total per Day |  |  |  | 38 | 35 | 35 | 26 | 24 | 22 | 11 | 0
1st Sprint Bug Fix | Don't allow state changes in the OccupiedState | Bug-Fix | Alexandre | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Fix video calls | Bug-Fix | Rodrigo | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1st Sprint Refination | Provide interface for LastMadeCommunication | Domain | Alexandre | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Move SendSMS behaviour to the PhoneState | Domain | Rodrigo | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Organize exceptions in packages | Domain | Joaquim | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Replace substrings to get number prefixes | Domain | Alexandre | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Refine GetLastMadeCommunicationService | Service | Alexandre | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Turn representations and verifiers into Singletons | Service | João | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | M | T | W | R | F | S | S
| Organize and improve tests | Testing | Miguel | 3 | 2 | 2 | 1 | 0 | 0 | 0 | 0 |  | Estimate | 2012-04-23 | 2012-04-24 | 2012-04-25 | 2012-04-26 | 2012-04-27 | 2012-04-28 | 2012-04-29
| Display error messages more appropriately | Presentation | João | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | Ideal | 38 | 30.4 | 22.8 | 15.2 | 7.6 | 0 | 0 | 0
| Improve communication input and last communication display | Presentation | Rodrigo | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | Real | 38 | 35 | 35 | 26 | 24 | 22 | 11 | 0
UDDI Registry | Update build.xml | Distribution | Emídio e Rodrigo | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | Domain | 4 | 4 | 4 | 1 | 1 | 0 | 0 | 0
| Implemente registration, search and deletion | Distribution | Emídio e Rodrigo | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | Service | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Minimize UDDI searches | Distribution | Emídio e Rodrigo | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | Presentation | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
Timestamp Storing | Implement timestamp database | Distribution | Miguel e Rodrigo | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | Distribution | 24 | 24 | 24 | 21 | 20 | 19 | 8 | 0
| Implement handlers | Distribution | Emídio e Miguel | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | Testing | 3 | 2 | 2 | 1 | 0 | 0 | 0 | 0
Packet Ordering | Number packets | Distribution | Miguel | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | Bug-Fix | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Order packets | Distribution | Miguel | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
Certification Authority | Implement database | Distribution | Alexandre e João | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 0
| Implement SignCertificateService | Distribution | João e Joaquim | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0
| Write WSDL | Distribution | Alexandre e Joaquim | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
Note on C3: SMART Tasks: - Specific - Measurable - Achievable - Relevant - Time-Boxed

## 3rd Sprint
|  |  |  | 23 | M | T | W | R | F | S | S
Story | Task | Category | Who | 5 | Time to finish task (person/hour)
|  |  |  | Estimate | 2012-04-30 | 2012-05-01 | 2012-05-02 | 2012-05-03 | 2012-05-04 | 2012-05-05 | 2012-05-06
Ideal Execution |  |  |  | 32 | 25.6 | 19.2 | 12.8 | 6.4 | 1.7764e-15 | 0 | 0
Total per Day |  |  |  | 32 | 21 | 19 | 19 | 14 | 12 | 12 | 0
Silent Failures | Implement packet replicator | Distribution | Emídio e Miguel | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
| Implement response merger | Distribution | Miguel e Rodrigo | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 0
| Implement asynchronous calls | Distribution | Emídio e Rodrigo | 3 | 3 | 1 | 1 | 0 | 0 | 0 | 0
Message Authentication | Check certificate's time validity | Distribution | Joaquim | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Validate CA's certificate | Distribution | João | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Validate client's digital signature | Distribution | Alexandre e Joaquim | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 |  |  | M | T | W | R | F | S | S
Certificate Revogation | Implement RevogateCertificateService | Distribution | Alexandre e João | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Estimate | 2012-04-30 | 2012-05-01 | 2012-05-02 | 2012-05-03 | 2012-05-04 | 2012-05-05 | 2012-05-06
| Implement GetBlackListService | Distribution | João e Joaquim | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Update WSDL | Distribution | João e Joaquim | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | Ideal | 32 | 25.6 | 19.2 | 12.8 | 6.4 | 1.7764e-15 | 0 | 0
| Verify if certificates aren't in black list | Distribution | Alexandre e João | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 0 | Real | 32 | 21 | 19 | 19 | 14 | 12 | 12 | 0
Timestamp Phones | Update Domain | Domain | Miguel | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Domain | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Update Services | Service | Rodrigo | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Service | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Update WSDL | Distribution | Rodrigo | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Presentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Distribution | 27 | 21 | 19 | 19 | 14 | 12 | 12 | 0
[12 empty] | Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Bug-Fix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on C3: SMART Tasks: - Specific - Measurable - Achievable - Relevant - Time-Boxed

## 4th Sprint
|  |  |  | 27 | M | T | W | R | F | S | S
Story | Task | Category | Who | 5 | Time to finish task (person/hour)
|  |  |  | Estimate | 2012-05-07 | 2012-05-08 | 2012-05-09 | 2012-05-10 | 2012-05-11 | 2012-05-12 | 2012-05-13
Ideal Execution |  |  |  | 56 | 44.8 | 33.6 | 22.4 | 11.2 | 0 | 0 | 0
Total per Day |  |  |  | 56 | 47 | 40 | 36 | 26 | 18 | 7 | 0
Byzantine Failures | Implement response voting | Distribution | Emídio e Rodrigo | 5 | 5 | 5 | 5 | 3 | 3 | 0 | 0
| Ignore multiple response from the same server | Distribution | Emídio e Miguel | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 0
Refine Timestamping | Update domain | Domain | Miguel | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Update services | Service | Emídio e Miguel | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Implement SetTimestampService and GetTimestampService | Service | Emídio e Miguel | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Update ApplicationServerWebService | Distribution | Emídio e Rodrigo | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Update DistributedAnacomServerBridge | Distribution | Emídio e Rodrigo | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | M | T | W | R | F | S | S
Replication Tests | Test packet replication | Testing | Emídio e Miguel | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 |  | Estimate | 2012-05-07 | 2012-05-08 | 2012-05-09 | 2012-05-10 | 2012-05-11 | 2012-05-12 | 2012-05-13
| Test packet merging | Testing | Miguel e Rodrigo | 3 | 3 | 3 | 2 | 2 | 1 | 0 | 0
| Test silent fault toleration | Testing | Emídio e Miguel | 6 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | Ideal | 56 | 44.8 | 33.6 | 22.4 | 11.2 | 0 | 0 | 0
| Test byzantine fault toleration | Testing | Emídio e Rodrigo | 6 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | Real | 56 | 47 | 40 | 36 | 26 | 18 | 7 | 0
Security Tests | Test SetKeysService | Testing | Joaquim | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Domain | 5 | 3 | 3 | 3 | 3 | 2 | 0 | 0
| Test SignCertificateService | Testing | Joaquim | 5 | 5 | 4 | 4 | 0 | 0 | 0 | 0 | Service | 3 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Test BlockCertificateService | Testing | Alexandre | 4 | 4 | 3 | 3 | 3 | 3 | 2 | 0 | Presentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Test GetBlockedListService | Testing | João | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 0 | Distribution | 10 | 7 | 7 | 7 | 4 | 4 | 1 | 0
| Test SOAP messages | Testing | Alexandre e João | 6 | 6 | 5 | 5 | 4 | 4 | 3 | 0 | Testing | 36 | 34 | 27 | 23 | 16 | 12 | 6 | 0
3rd Sprint Refination | Add type distinction in the communication classes | Domain | Alexandre | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | Bug-Fix | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
| Normalize prefix determination | Domain | Joaquim | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| Normalize attribute names | Bug-Fix | João | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
| Normalize service return | Service | Joaquim | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Note on C3: SMART Tasks: - Specific - Measurable - Achievable - Relevant - Time-Boxed

## 5th Sprint
|  |  |  | 17 | M | T | W | R | F | S | S
Story | Task | Category | Who | 2 | Time to finish task (person/hour)
|  |  |  | Estimate | 2012-05-14 | 2012-05-15 | 2012-05-16 | 2012-05-17 | 2012-05-18 | 2012-05-19 | 2012-05-20
Ideal Execution |  |  |  | 9 | 4.5 | 0
Total per Day |  |  |  | 9 | 5 | 0
Bug Fix | Fix replication bugs | Bug-Fix | ALL | 1 | 1 | 0
| Fix order packet bugs | Bug-Fix | ALL | 1 | 1 | 0
| Fix SecurityHandler bugs | Bug-Fix | ALL | 1 | 1 | 0
| Fix CAManager bugs | Bug-Fix | ALL | 1 | 0 | 0
Refactoring | SecurityHandler refactoring | Bug-Fix | ALL | 1 | 0 | 0
| BizantineProtocolHandler refactoring | Bug-Fix | ALL | 1 | 0 | 0
| SilentFailureProtocolHandler refactoring | Bug-Fix | ALL | 1 | 0 | 0 | [7 empty] | M | T | W | R | F | S | S
Write Reports | Write ES report | Bug-Fix | ALL | 1 | 1 | 0 | [6 empty] | Estimate | 2012-05-14 | 2012-05-15 | 2012-05-16 | 2012-05-17 | 2012-05-18 | 2012-05-19 | 2012-05-20
| Write SD report | Bug-Fix | ALL | 1 | 1 | 0
[12 empty] | Ideal | 9 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Real | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Domain | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Service | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Presentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Distribution | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Bug-Fix | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0
Note on C3: SMART Tasks: - Specific - Measurable - Achievable - Relevant - Time-Boxed

## Check
Fibonnaci | Status | Category | Person
0 | Dropped | Domain | Alexandre
0.5 | Done! | Service | Emídio
1 | Blocked | Presentation | João
2 | Ongoing | Distribution | Joaquim
3 | Planned | Testing | Miguel
5 |  | Bug-Fix | Rodrigo
8 |  |  | Joaquim e Rodrigo
13 |  |  | Alexandre e Emídio
21 |  |  | João e Miguel
34 |  |  | Emídio e Rodrigo
55 |  |  | Miguel e Rodrigo
89 |  |  | Emídio e Miguel
∞ |  |  | Alexandre e João
Alexandre e Joaquim
João e Joaquim
ALL